JOINT DELIVERY PLAYBOOK

Restaurant QR Platform

Production Delivery Plan for Yazan & Alaa

| Plan metadata | Current agreement |
| --- | --- |
| Version | 1.0 — execution baseline |
| Date | 13 August 2026 |
| Working baseline | codex/tenant-transition — commit 76de5f1 |
| Product scope | Multi-tenant restaurant QR menu, ordering, administration, and platform operations |
| Production target | Secure, observable, recoverable SaaS with staging and controlled releases |

Mission: Finish one dependable product together. Yazan owns platform correctness and production operations; Alaa owns product experience and frontend quality. Neither area ships without review from the other.

# How to use this plan

- Treat ownership as accountability, not exclusivity: the directly responsible individual drives the result and requests review early.

- Work milestone by milestone. A milestone is complete only when its acceptance gate, tests, documentation, and deployment evidence are complete.

- Review this plan every Monday, update risks and commitments, and record any scope decision in the repository.

- Do not add POS back into this release. It remains a separate future product stream unless both owners approve a new scope and architecture plan.

# 1. Product outcome and release boundary

The production release is a multi-tenant restaurant SaaS. A restaurant organization can have multiple users and branches; owners manage access, restaurant staff manage the catalog and orders, customers scan table QR codes and place orders, and the platform SuperAdmin manages restaurants and plans.

## Release 1 must include

- Tenant onboarding: organization, branch, owner identity, memberships, roles, session restoration, and organization switching.

- Restaurant administration: profile, branding, menu categories, products, ingredients, modifiers, combos, availability, pricing, promotions, tables, and QR generation.

- Customer ordering: English and Arabic, RTL/LTR, menu discovery, customization, cart, dine-in/takeaway, pricing, order submission, confirmation, and status tracking.

- Operations: order queue, valid workflow transitions, notes and modifiers, real-time updates, reconnect behavior, analytics, exports, and settings.

- Platform administration: SuperAdmin authentication, restaurant overview, subscription limits, plan updates, health checks, and safe tenant support workflows.

- Production foundation: staging, CI checks, migrations, backups, object storage, monitoring, alerting, secrets, rollback, runbooks, and release evidence.

## Explicitly outside Release 1

- POS, cash drawers, till shifts, card-present payments, and receipt hardware.

- Native mobile applications; the customer and admin experiences remain responsive web applications.

- Marketplace integrations, delivery aggregators, accounting sync, and advanced loyalty unless re-prioritized after pilot feedback.

## Release success measures

| Measure | Release target | Evidence owner |
| --- | --- | --- |
| Core journey | 100% pass: owner signup → menu → QR → customer order → status completion | Alaa, reviewed by Yazan |
| Tenant isolation | No cross-organization read/write access in API and socket tests | Yazan, reviewed by Alaa |
| Reliability | No P0/P1 defects; rollback and restore rehearsed in staging | Yazan |
| Experience | Mobile/desktop, English/Arabic, keyboard and screen-reader critical paths pass | Alaa |

# 2. Ownership model

Decision rule: The DRI decides implementation details inside an agreed contract. Product scope, schema breaking changes, security posture, and production releases require both Yazan and Alaa.

## Yazan — Platform, architecture, backend, and operations lead

- Own system architecture, tenant boundaries, authentication, authorization, data integrity, API contracts, Socket.IO security, and migration safety.

- Own PostgreSQL/Prisma schema evolution, indexes, transactions, backups, restore testing, and production data operations.

- Own backend modularization, validation, rate limiting, structured errors, observability, deployment automation, environments, and incident response.

- Own security engineering: secrets, password/session policy, access control, upload security, dependency review, and audit logging.

- Approve frontend work that changes API contracts, tenant context, order totals, security, or production operations.

## Alaa — Product, frontend, UX, accessibility, and functional QA lead

- Own user journeys, information architecture, design system, responsive behavior, Arabic/English experience, accessibility, and UI consistency.

- Own customer menu, cart/customization, order confirmation/tracking, admin workspace, team-management UI, analytics presentation, and SuperAdmin UX.

- Own frontend state, loading/error/empty states, browser lifecycle recovery, optimistic behavior, route-level performance, image presentation, and client analytics.

- Own acceptance scenarios, cross-device exploratory testing, E2E automation, regression evidence, and user-facing documentation.

- Approve backend work that changes user behavior, validation messages, role capabilities, or critical workflow semantics.

## Responsibility matrix

| Area | DRI | Required reviewer | Definition of outcome |
| --- | --- | --- | --- |
| Tenant/auth/data | Yazan | Alaa | Safe multi-user tenant isolation |
| API/realtime | Yazan | Alaa | Stable documented contracts and reconnect behavior |
| Customer menu/cart | Alaa | Yazan | Fast, accessible, correct ordering |
| Admin/team UI | Alaa | Yazan | Role-aware operational workspace |
| Database/migrations | Yazan | Alaa | Expand/backfill/verify/contract changes |
| Testing | Alaa: E2E | Yazan: API/integration | One shared release report |
| Security/operations | Yazan | Alaa | Threat model, alerts, runbooks |
| Release decision | Both | Both | Written Go / No-Go |

## Interface handoff protocol

- Before implementation, agree the user outcome, API or component contract, validation rules, and acceptance evidence in the ticket.

- The DRI publishes an early draft when the reviewer can still influence the design; review is not delayed until the feature is finished.

- The reviewer responds within one working day or explicitly records when review will happen. A blocker is raised in the daily update.

- If Yazan and Alaa disagree, tenant safety and data integrity take precedence, then validated user evidence, then implementation preference.

# 3. Engineering workflow and collaboration contract

## Branches and pull requests

- main is production only. No direct pushes. Every change arrives through a reviewed pull request.

- develop is the staging integration branch after tenant-transition is accepted. Production releases merge develop into main through a release PR.

- Use yazan/<ticket>-<short-name> and alaa/<ticket>-<short-name> for feature branches. Rebase or merge develop before final review.

- Keep PRs small enough to review in one focused session. Split schema, API, and UI changes when doing so reduces risk.

- Every PR includes: problem, solution, screenshots or API evidence, tests run, migration impact, security impact, and rollback note.

## Required review rules

- No author self-merges a production-critical PR.

- Yazan reviews authentication, authorization, schema, migrations, totals, uploads, sockets, deployment, and secrets.

- Alaa reviews customer/admin behavior, responsive layouts, language, accessibility, copy, loading/error states, and end-to-end flows.

- Breaking API changes require a written contract and coordinated frontend/backend rollout.

- Migration PRs must include forward validation, data backfill checks, expected locks/duration, and rollback or mitigation steps.

## Weekly operating rhythm

| When | Activity | Output |
| --- | --- | --- |
| Monday | 30-minute planning and risk review | Committed tickets, owners, acceptance criteria |
| Daily | 10-minute async update: done / next / blocked | Visible progress and early escalation |
| Wednesday | Integration checkpoint | Contracts aligned; staging remains deployable |
| Friday | Demo, regression, metrics, and retrospective | Release evidence and next-week adjustments |
| Before release | Go / No-Go review | Signed checklist, owner, rollback window |

# 4. Target production architecture

The application remains a single deployable web service initially, but its internal boundaries must be explicit. The frontend is React/Vite/TypeScript; the backend is Node/Express with Socket.IO; Prisma accesses PostgreSQL. Render can host staging and production, but production must use a paid always-on service and a database plan with backups.

## Required request and data flow

- Browser loads versioned static assets from the application domain or CDN.

- Authenticated request carries a short-lived signed identity and organization context.

- Middleware resolves User → OrganizationUser → Organization and selects the compatibility restaurant profile during migration.

- Service layer validates input, authorization, workflow state, and tenant ownership before database access.

- Database query includes organization ownership; transactions protect totals, promotions, order creation, and state changes.

- Socket rooms are joined only after the same membership/tenant authorization check.

- Structured logs, traces/metrics, and error reporting record request ID, organization ID, route, duration, and safe error context.

## Architecture work Yazan must complete

- Tenant transition phase 2: add direct organization_id ownership to catalog, tables, orders, promotions, uploads, and audit records; backfill and index it; then update all queries.

- Make Admin a restaurant profile rather than an identity. Stop authenticating against Admin.password after the compatibility window and plan its removal.

- Split server/index.js into routers, controllers, domain services, validation schemas, middleware, repositories, and centralized error handling.

- Replace in-memory rate limiting with a shared production store; add idempotency to public order creation and sensitive writes.

- Move uploads from local Render disk to managed object storage with signed upload rules, size/type verification, lifecycle, and deletion ownership.

- Standardize API versioning, pagination, response envelopes, correlation IDs, and OpenAPI documentation.

## Architecture work Alaa must complete

- Create a typed frontend API boundary and eliminate duplicate/stale schema files and unused authentication hooks.

- Implement organization switcher and team member UI with owner/manager/staff capability guards.

- Create reusable route-level error boundaries, skeletons, empty states, retry behavior, and offline/reconnect messaging.

- Separate large pages into feature modules and lazy-loaded routes; keep critical customer menu code small and cache-safe.

- Create a single design token/component contract for spacing, typography, forms, dialogs, cards, status chips, and dark/RTL modes.

# 5. Delivery roadmap and milestone gates

Planning assumption: Two active contributors, ten focused weeks, weekly staging demos, and no major POS or payment-scope expansion. Dates move when quality gates fail; gates do not get waived.

| Window | Milestone | Primary work | Exit gate |
| --- | --- | --- | --- |
| M0 • Week 1 | Baseline and contracts | Yazan: architecture records, environments, CI skeleton. Alaa: flow inventory, design audit, acceptance suite. | Build, lint, tests, staging deploy; agreed backlog and API contracts. |
| M1 • Weeks 1–2 | Tenant completion | Yazan: direct tenant ownership plan, auth/member hardening. Alaa: team and organization-switch UX. | Two users share one tenant; cross-tenant tests fail closed; legacy IDs still work. |
| M2 • Weeks 3–4 | Core restaurant cycle | Yazan: order/catalog validation, idempotency, socket rules. Alaa: onboarding, menu, QR, customer order, order board polish. | Golden journey passes on mobile/desktop, EN/AR, refresh/reconnect. |
| M3 • Weeks 5–6 | Production infrastructure | Yazan: object storage, shared limiter, logs/errors, backups, staging/prod separation. Alaa: observability events, performance and accessibility fixes. | Restore rehearsal, alerts, secure uploads, stable staging. |
| M4 • Weeks 7–8 | Quality hardening | Yazan: API/integration/security/performance tests. Alaa: E2E/browser/device regression and UX defect closure. | No P0/P1, migration rehearsal, target SLO evidence. |
| M5 • Week 9 | Pilot | Both: onboard 1–3 controlled restaurants, monitor, collect feedback, fix release blockers. | Seven stable pilot days; support and rollback runbooks proven. |
| M6 • Week 10 | Production launch | Both: backup, release, smoke tests, monitoring, support rotation, post-launch review. | Go decision recorded; metrics healthy; rollback window closed. |

# 6. Detailed work plan — Yazan

| Priority | Workstream | Deliverable | Acceptance evidence |
| --- | --- | --- | --- |
| P0 | Tenant phase 2 | Organization-owned columns, backfill, indexes, query enforcement, migration report | Cross-tenant integration suite |
| P0 | Authentication | Session policy, membership validation, token rotation/expiry decision, safe logout | Expired/suspended/switched tenant tests |
| P0 | Order integrity | Idempotency key, server totals, promotion transaction, status concurrency | Duplicate and race tests |
| P0 | Production data | Managed Postgres, backup/PITR, restore runbook, migration rehearsal | Timed staging restore |
| P0 | Uploads | Managed object storage and ownership-safe deletion | Malicious file and persistence tests |
| P1 | Backend structure | Routers/services/validators/errors; remove monolithic route coupling | Module-level integration tests |
| P1 | Realtime | Authenticated joins, reconnect strategy, event versioning, delivery expectations | Disconnect/resume/multi-tab tests |
| P1 | Observability | Structured logs, Sentry-equivalent errors, health, alerts, dashboards | Synthetic failure alert |
| P1 | CI/CD | Protected branches, checks, staging deploy, migration gate, rollback | Failed check blocks merge |
| P2 | Performance | Query plans, indexes, pagination, caching, connection pool | Load test report |

## Yazan’s non-negotiable handoff artifacts

- OpenAPI or equivalent endpoint contract with auth, payload, errors, and examples.

- Migration README for every data-changing release, including backfill verification queries.

- Environment variable inventory with owner, purpose, required/optional status, and rotation procedure—never secret values.

- Production runbooks for deploy, rollback, database restore, tenant suspension, and incident triage.

- API/integration test report linked in each milestone PR.

# 7. Detailed work plan — Alaa

| Priority | Workstream | Deliverable | Acceptance evidence |
| --- | --- | --- | --- |
| P0 | Golden journey | Owner onboarding through completed customer order | E2E on mobile and desktop |
| P0 | Tenant UX | Organization switcher, members, roles, access-denied behavior | Owner/manager/staff scenarios |
| P0 | Order continuity | Refresh/background/reconnect state persistence and clear recovery | Mobile lifecycle test |
| P0 | Responsive/RTL | No overflow; correct hierarchy and gestures in EN/AR | Viewport matrix and screenshots |
| P1 | Design system | Tokens and reusable controls; consistent dark/light modes | Component inventory and QA |
| P1 | Accessibility | Labels, focus, keyboard, contrast, dialogs, announcements | Automated + manual WCAG checks |
| P1 | Frontend reliability | Error boundaries, skeletons, retries, empty/offline states | Injected failure scenarios |
| P1 | Performance | Route splitting, image strategy, request deduplication, render profiling | Lighthouse and bundle report |
| P1 | Admin operations | Menu, QR, orders, settings, analytics, SuperAdmin polish | Role-based regression suite |
| P2 | Documentation | Operator quick start, restaurant onboarding, troubleshooting | Pilot user completes unaided |

## Alaa’s non-negotiable handoff artifacts

- Annotated screenshots or short recordings for every significant UI PR.

- Acceptance scenarios covering success, loading, empty, validation, permission, network, and server-failure states.

- Device/browser matrix covering iOS Safari, Android Chrome, and current desktop Chrome/Firefox/Safari where available.

- Accessibility and performance reports for customer menu, authentication, admin orders, and team management.

- Release notes and operator documentation updated before Go / No-Go.

# 8. Critical user journeys and acceptance gates

| Journey | Scenario | Pass condition |
| --- | --- | --- |
| Tenant owner | Sign up → organization/main branch created → session restored → profile configured | No partial records; reload stays signed in |
| Team | Owner adds manager → manager signs in → same tenant data → restricted owner action blocked | Shared data and least privilege |
| Catalog | Create category/item/options → upload image → publish → customer sees exact configuration | No stale or cross-tenant content |
| QR/table | Create table → generate/download/scan QR → correct restaurant and table open | Deep link works after refresh |
| Customer order | Customize → notes → cart → promotion/tip → submit once → confirmation | Server totals match; duplicate click creates one order |
| Kitchen/admin | New order arrives live → valid transitions → customer tracking updates | Reconnect catches up without status loss |
| Analytics | Completed/cancelled test orders produce correct summaries and export | Totals reconcile with database |
| SuperAdmin | Sign in → inspect restaurants → update plan/limits → tenant sees enforcement | No restaurant can access platform routes |

## Shared functional rules

- All prices and totals are calculated and validated on the server using decimal-safe rules; client totals are previews only.

- Every tenant-protected read and write fails closed when organization membership is absent, inactive, or mismatched.

- Order state transitions follow one server-owned state machine and are safe under concurrent updates.

- Customer tracking reveals only the minimum order information required and uses scoped, expiring credentials.

- Every destructive action requires explicit confirmation, ownership validation, and an audit event where appropriate.

# 9. Test strategy

| Layer | Coverage | When | DRI |
| --- | --- | --- | --- |
| Unit | Totals, roles, state transitions, validators, formatters | On every PR | Shared |
| API integration | Auth, tenant isolation, catalog, orders, promotions, uploads | On every backend PR | Yazan |
| Migration | Fresh DB, production-like backfill, rerun safety, verification counts | Every migration PR | Yazan |
| Component | Forms, modals, cards, RTL, error and loading states | On frontend PR | Alaa |
| E2E | Golden journeys and role matrix | PR smoke + nightly full | Alaa |
| Security | IDOR, auth bypass, upload, CORS, rate limits, socket rooms | Each milestone | Yazan |
| Performance | Public menu, order submit, order queue, large catalog | M3 onward | Shared |
| Recovery | DB restore, failed deploy, socket/network interruption | Before pilot/release | Shared |

## Minimum PR checks

- npm ci, Prisma generate/validate, migration status or disposable-database migration test.

- TypeScript production build, ESLint with zero errors, unit tests, affected integration tests, and affected E2E smoke.

- Dependency and secret scanning; no credentials, production data, database dumps, or local .env files in Git.

- Visual review for UI changes and explicit evidence for mobile, RTL, dark mode, and accessibility when affected.

## Defect severity

| Level | Meaning | Release rule |
| --- | --- | --- |
| P0 | Data loss, tenant leak, credential/payment compromise, full outage | Stop work/release; immediate incident response |
| P1 | Core signup, menu, order, admin, or deployment path broken | No release |
| P2 | Important function degraded with workaround | Owner-approved only; scheduled fix |
| P3 | Minor visual/copy/usability issue | May enter backlog |

# 10. Security and privacy gate

## Yazan must verify

- Passwords use strong hashing; authentication errors avoid account enumeration; tokens have expiry and safe secret rotation.

- Every protected endpoint and socket room validates user, active membership, organization, role, and resource ownership.

- CORS, CSP, HSTS, security headers, upload signatures, file size/type, filename handling, and object access are production-safe.

- Rate limits cover login, signup, public ordering, tracking, promotion validation, uploads, and expensive queries using a shared store.

- Logs exclude passwords, tokens, connection strings, customer notes where unnecessary, and full request bodies containing sensitive data.

- Dependencies are reviewed; critical vulnerabilities have a documented fix or explicit risk acceptance before release.

## Alaa must verify

- The UI never exposes controls or tenant data for unauthorized roles and handles 401/403 without leaking details.

- User-supplied names, descriptions, URLs, and notes render safely; no unsafe HTML injection is introduced.

- Sensitive values do not appear in URLs, analytics events, screenshots, browser logs, or persisted client state.

- Destructive actions are clear, scoped, confirmed, and resistant to accidental double submission.

- Privacy copy states what restaurant/customer data is collected, why, how long it is retained, and how deletion requests are handled.

Launch blocker: Any reproducible cross-tenant access, authentication bypass, destructive migration risk, exposed secret, or unbounded public write is an automatic No-Go.

# 11. Performance, reliability, and observability

| Signal | Initial target | Action when breached |
| --- | --- | --- |
| Availability | 99.9% monthly after paid production hosting | Incident review and capacity/reliability fix |
| Warm API latency | p95 < 500 ms; order submit p95 < 800 ms | Trace slow route/query; index or simplify |
| Public menu | LCP < 2.5 s; CLS < 0.1 on representative mobile | Reduce JS/images and request waterfalls |
| Error rate | < 1% 5xx over 15 minutes | Alert Yazan; assess rollback |
| Realtime | Reconnect and state catch-up within 10 seconds | Fallback refresh/poll and investigate |
| Database | Backups successful daily; restore objective proven | Stop release until restore confidence returns |

## Production telemetry

- Structured backend logs with timestamp, request ID, route, status, duration, organization ID, user ID, and safe error code.

- Frontend error reporting with release version, route, browser, organization ID where safe, and source maps protected from public listing.

- Dashboards for request volume/latency/errors, database connections/slow queries, order creation/status transitions, socket connections, and deployment version.

- Alerts for health/readiness failure, elevated 5xx, failed migrations, database saturation, backup failure, and order submission anomalies.

## Known current risks to close

- Render free instances sleep and are not an acceptable production reliability target.

- Local filesystem uploads are ephemeral on Render and must be replaced before production.

- The current in-memory rate limiter does not coordinate across instances and loses state on restart.

- Automated test coverage is still small; the current five tests are a foundation, not a release suite.

- Large PDF/chart bundles need route-level loading and measurement to protect customer-menu performance.

# 12. Environments, deployment, and rollback

| Environment | Purpose | Data rule | Deployment |
| --- | --- | --- | --- |
| Local | Daily development | Synthetic only; developers may reset | Manual developer commands |
| Staging | Integration, migration rehearsal, QA, pilot rehearsal | Synthetic/anonymized; never copied production secrets | Auto-deploy develop after CI |
| Production | Live restaurant/customer traffic | Controlled access, backups, retention policy | Approved release PR/tag only |

## Release procedure

- Freeze scope and generate release candidate from develop; all required checks pass.

- Verify recent backup and record rollback owner, migration impact, release version, and maintenance expectations.

- Deploy the exact candidate to staging, run migrations, smoke all critical journeys, and observe for the agreed soak period.

- Approve Go / No-Go together; merge/tag the release and deploy production during a staffed window.

- Run health, authentication, tenant, menu, QR, order, realtime, analytics, and SuperAdmin smoke checks.

- Monitor errors, latency, database, and order metrics through the rollback window; announce completion only after stability is confirmed.

## Migration policy

- Use expand → deploy compatible code → backfill/verify → enforce → contract. Never combine a destructive contract step with unproven code.

- Do not edit an already applied migration. Add a new migration and test it from both an empty database and a production-like snapshot.

- Large backfills run in bounded batches with progress and verification; understand locks before production.

- Rollback favors application rollback plus forward database repair when a migration cannot safely be reversed.

# 13. Definition of Done

A task is done only when every applicable condition below is true. ‘Works on my machine’ and ‘code is written’ are not completion states.

- Acceptance criteria and error/permission cases are implemented and demonstrated.

- Tenant ownership, role authorization, input validation, and audit requirements are reviewed.

- Automated tests cover the changed domain and pass in CI; manual evidence is attached where automation is insufficient.

- Mobile, desktop, English, Arabic/RTL, loading, empty, error, offline/reconnect, and accessibility impacts are checked.

- Performance impact is measured for critical paths; avoid new request waterfalls, large eager bundles, N+1 queries, or unbounded results.

- Migrations are reviewed and verified; no production data or secrets are present in code, logs, fixtures, or screenshots.

- Documentation, API contracts, environment inventory, release notes, and runbooks are updated as applicable.

- The non-author reviews and approves; staging is green; rollback/mitigation is understood.

## Go / No-Go checklist

| Gate | Required evidence | Owner |
| --- | --- | --- |
| Product | All critical journeys pass; no P0/P1 | Alaa |
| Tenant/security | Isolation and role matrix pass; security review closed | Yazan |
| Data | Migration rehearsal, backup, restore verification | Yazan |
| Performance | Targets measured and accepted | Shared |
| Operations | Monitoring, alerts, runbooks, support coverage | Yazan |
| Experience | Mobile/RTL/accessibility/browser matrix | Alaa |
| Decision | Written Go approval and rollback owner | Both |

# 14. First 14 days — concrete assignments

## Yazan

- Publish architecture decision records for tenant ownership, Admin-profile deprecation, session strategy, object storage, and environment topology.

- Add CI with install, Prisma validate/generate, disposable-database migrations, lint, tests, build, dependency scan, and secret scan.

- Design and implement tenant phase-2 expand migration plus verification queries; do not remove compatibility columns yet.

- Create API contract for organization members/switching and order idempotency; add cross-tenant and role integration tests.

- Create staging services/database, environment inventory, structured logging baseline, and backup/restore rehearsal plan.

## Alaa

- Map every customer, admin, team, and SuperAdmin screen with success/loading/empty/error/permission states.

- Build organization switcher and team member management UI against the tenant-transition APIs, including owner/manager/staff restrictions.

- Create the golden E2E skeleton and automate signup, login, menu creation, QR deep link, customer order, and order status flow.

- Complete a responsive/RTL/accessibility audit of authentication, customer menu, admin navigation, orders, QR, and team UI; file prioritized issues.

- Define shared frontend tokens/components and capture baseline bundle/Lighthouse measurements before optimization.

## Joint outputs by Day 14

- A green CI pipeline and continuously deployable staging environment.

- An agreed API/UX tenant contract and demonstrated owner + manager shared-restaurant flow.

- A prioritized release backlog with P0/P1/P2 severity, acceptance criteria, owner, reviewer, and milestone.

- A recorded golden-journey demo and a short risk register with mitigation owners and due dates.

# 15. Risk register and decision log

| Risk | Impact | Mitigation | Owner |
| --- | --- | --- | --- |
| Tenant transition remains half-complete | Cross-user inconsistency or leakage | Direct organization ownership, dual-read/write checks, isolation tests | Yazan |
| Two-person bottleneck | Review and delivery delays | Small PRs, explicit DRI, WIP limit, early contract reviews | Both |
| Production on free infrastructure | Cold starts and weak reliability | Paid always-on service and managed DB before pilot | Yazan |
| Insufficient regression coverage | Repeated defects and unsafe releases | Golden E2E plus API/migration suites as milestone gates | Alaa / Yazan |
| Scope expands into POS/payments | Roadmap failure | Release boundary and written change decision | Both |
| Upload/data handling gaps | Lost assets or security incident | Object storage, ownership, scanning, retention and privacy policy | Yazan |

## Decisions both must make before Milestone 1 closes

- Will the product support one or multiple branches in Release 1 UI, even though the data model supports branches?

- What is the exact invitation flow: temporary password, email invitation, or administrator-created credential?

- What customer data is retained, for how long, and what deletion/export policy will be promised?

- Which production providers will be used for object storage, error monitoring, transactional email, and shared rate limiting?

- Which pricing/subscription limits are real and enforced at launch, and which remain hidden until billing exists?

- What is the pilot cohort, support channel, staffed release window, and acceptable rollback duration?

# Working agreement sign-off

| Owner | Commitment | Review date |
| --- | --- | --- |
| Yazan | I own platform correctness, tenant safety, data, security, and production operations. | ________________ |
| Alaa | I own product completeness, frontend quality, accessibility, and functional release evidence. | ________________ |
| Both | We protect scope, review each other’s critical work, and ship only when the release gates pass. | ________________ |

Final principle: Move quickly by keeping the system releasable every week. Quality, tenant safety, and recoverability are product features—not work postponed until launch.

## Plan maintenance

- Review commitments, risks, and milestone evidence every Monday; record changes in the repository.

- Create a new document version whenever scope, ownership, architecture, or release gates materially change.

- Use tickets and pull requests as the source of truth for daily execution; this plan controls direction and accountability.

- Archive superseded versions rather than silently rewriting history after a release decision.